## W5
PROJECT REPORT
Group | Restaurant Management Team
Week | 17/2/2025 - 12/2/2025
I. Status Report
# | Project Task | Status | Notes (Work Item in Details)
1 | Design database | In Progress
2 | Check diagram in doc | Completed
3 | Code register function | In Progress
4 | Code login function | In Progress
II. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Code UI for login | 2025-02-28
2 | Code UI for homepage | 2025-02-28