## W1
PROJECT REPORT
Group | restaurant-management
Week | 10/02/2025 - 16/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Database Design | All Team | In Progress
2 | Check diagram in doc | All Team | In Progress
3 | Write testcase in my task | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Slow progress in Coding | All Team | In Progress | Team meeting
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Front-end Design | All team | 2025-02-26
2 | Code enity funition | All team | 3/4/025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Weekly group meeting suggestions | Team Lead | 2025-02-22 | Make sure to keep information updated