## Sheet1
Date | Duration (h) | Topic | Status
T3, 07-Thg1 | 8 | Mock Project - Slot 1 - Kick off Project Introduction | Started
T5, -09Thg1 | 8 | Mock Project - Slot 2 - Project Management Plan | To Do
T3, 14-Thg1 | 8 | Mock Project - Slot 3 - Create Software Requirement Specification
T5, 16-Thg1 | 8 | Mock Project - Slot 4 - Review and update SRS
T3, 21-Thg1 | 8 | Mock Project - Slot 5 - Database Design
T5, 06-Thg2 | 8 | Mock Project - Slot 6 - Review and update SDD
T3, 11-Thg2 | 8 | Mock Project - Slot 7 - Create Test plan, Testcase
T5, 13-Thg2 | 8 | Mock Project - Slot 8 - Review and update TC
T3, 18-Thg2 | 8 | Mock Project - Slot 9 - Coding
T5, 20-Thg2 | 8 | Mock Project - Slot 10 - Coding
T3, 25-Thg2 | 8 | Mock Project - Slot 11 - Coding
T5, 27-Thg2 | 8 | Mock Project - Slot 12 - Coding
T3, 04-Thg3 | 8 | Mock Project - Slot 13 - Coding
T5, 06-Thg3 | 8 | Mock Project - Slot 14 - Coding
T3, 11-Thg3 | 8 | Mock Project - Slot 15 - Review code + UT
T5, 13-Thg3 | 8 | Mock Project - Slot 16 - UT
T3, 18-Thg3 | 8 | Mock Project - Slot 17 - IT
T5, 20-Thg3 | 2 | Mock Project - Slot 18 - IT + Create Test Report
T3, 25-Thg3 | 2 | Mock Project - Slot 19 - Final Report
T5, 27-Thg3 | 4 | Mock Project - Slot 20 - Final Report (cont)
Topic: | Xây dựng website quản lý đặt chỗ nhà hàng
Dương Trí Khang- nhóm trưởng
Trần Quang Minh
Vương Đình Cương
Nguyễn Nhật Minh