## W1
PROJECT REPORT
Group | restaurant-management
Week | 03/02/2025 - 07/02/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Review and update SRS | All Team | Completed
2 | testcase | All Team | Completed
3 | Database Design | All Team | In Progress
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Slow progress in Database design | All Team | In Progress | Team meeting
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Front-end Design | All team | 2025-02-12
2 | Database Design | All team | 2025-02-13
3 | Review and update Blackbox TC | All team | 2025-02-14
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Weekly group meeting suggestions | Team Lead | 2025-02-08 | Make sure to keep information updated