## W1
PROJECT REPORT
Group | Restaurant management Team
Week | 10/2/2025 - 15/2/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Hoàn thành Project plan nộp BM và P. TCQLĐT | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Define SRS | Đình Cương | 2025-01-25
| Define design detail | Quang Minh | 2025-01-25
| Design usecase | Nhật Minh | 2025-01-25 | Usecase for guest, admin, chef, customer.
| Define project plan | Trí Khang | 2025-01-25 | Project workflow, check all
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W2
PROJECT REPORT
Group | Restaurant management Team
Week | 16/2/2025 - 22/2/2025 edit
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Hoàn thành Project plan nộp BM và P. TCQLĐT | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Define SRS | Đình Cương | 2025-01-17
| Define design detail | Quang Minh | 2025-01-17
| Design usecase | Nhật Minh | 2025-01-17 | Usecase for guest, admin, chef, customer.
| Define project plan | Trí Khang | 2025-01-17 | Project workflow
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes