## W6
PROJECT REPORT
Group | Restaurant Management Team
Week | 24/2/2025 - 1/3/2025
I. Status Report
# | Project Task | Status | Notes (Work Item in Details)
1 | Design database | Completed
2 | Code UI for login | In Progress
3 | Code register function | In Progress
II. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete login and register function | 2025-03-08
2 | Code UI for role manager | 2025-03-08