## Sheet1
Date | Duration (h) | Timeframe | Topic | Status
T3, 07-Thg1 | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off Project Introduction | Started
T5, -09Thg1 | 8 | 08:00-17:30 | Mock Project - Day 2 - Project Management Plan | To Do
T3, 14-Thg1 | 8 | 08:00-17:30 | Mock Project - Day 3 - Create Software Requirement Specification
T5, 16-Thg1 | 8 | 08:00-17:30 | Mock Project - Day 4 - Review and update SRS
T3, 21-Thg1 | 8 | 08:00-17:30 | Mock Project - Day 5 - Database Design
T5, 06-Thg02 | 8 | 08:00-17:30 | Mock Project - Day 6 - Review and update SDD
T3, 11-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 7 - Create Test plan, Testcase
T5, 13-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 8 - Review and update TC
T3, 18-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 9 - Coding
T5, 20-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 10 - Coding
T3, 25-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 11 - Coding
T5, 27-Thg2 | 8 | 08:00-17:30 | Mock Project - Day 12 - Coding
T3, 04-Thg3 | 8 | 08:00-17:30 | Mock Project - Day 13 - Coding
T5, 06-Thg3 | 8 | 08:00-17:30 | Mock Project - Day 14 - Coding
T3, 11-Thg3 | 8 | 08:00-17:30 | Mock Project - Day 15 - Review code + UT
T5, 13-Thg3 | 8 | 08:00-17:30 | Mock Project - Day 16 - UT
T3, 18-Thg3 | 8 | 08:00-17:30 | Mock Project - Day 17 - IT
T5, 20-Thg3 | 2 | 08:00-10:00 | Mock Project - Day 18 - IT + Create Test Report
T3, 25-Thg3 | 2 | 10:00-12:00 | Mock Project - Day 19 - Final Report
T5, 27-Thg3 | 4 | 13:30-17:30 | Mock Project - Day 20 - Final Report (cont)
Topic: | Xây dựng website quản lý đặt chỗ nhà hàng
Dương Trí Khang- nhóm trưởng
Trần Quang Minh
Vương Đình Cương